## Ind Project & 6 subprojects
Hour | Duration | Task Title | Start Date | End Date | Notes
26/09/2018 14:00 | 1.5 | Meeting with Jan | 2018-09-26 14:00 | 2018-09-26 15:30 | Meeting with Jan to discuss Summer progress and start to plan next few weeks. Agree to write down Use Cases for the resource folder, along with matching access policies. Start a research journal to match with Mendeley reference manager. Consider research notes through Sphinx? https://www.etsi.org/news-events/news/1341-1018-10-news-etsi-tc-cyber-hosts-webinar-series-for-european-cyber-security-month?platform=hootsuite https://github.com/zeutro/openabe http://siek.blogspot.com/2012/07/crash-course-on-notation-in-programming.html https://www.microsoft.com/en-us/research/academic-program/write-great-research-paper/ https://books.google.co.uk/books/about/How_to_Write_and_Publish_a_Scientific_Pa.html https://www.cs.umd.edu/%7Enspring/software/style-check-readme.html
27/09/2018 17:00 | 0.090278 | Investigate OCR for notes | 2018-09-27 17:56 | 2018-09-27 18:01
27/09/2018 18:00 | 1.0132 | Wrote up notes | 2018-09-27 18:27 | 2018-09-27 19:28
27/09/2018 19:00 | 0.21648 | Wrote up notes | 2018-09-27 19:28 | 2018-09-27 19:41
27/09/2018 21:00 | 0.48096 | Wrote up notes | 2018-09-27 21:51 | 2018-09-27 22:20
27/09/2018 22:00 | 0.41706 | Wrote up notes | 2018-09-27 22:43 | 2018-09-27 23:08
28/09/2018 13:00 | 0.46155 | Developing Use Cases | 2018-09-28 13:21 | 2018-09-28 13:49
28/09/2018 18:00 | 0.53882 | Developing Use Cases | 2018-09-28 18:29 | 2018-09-28 19:01
28/09/2018 19:00 | 0.40082 | Developing Use Cases | 2018-09-28 19:01 | 2018-09-28 19:25
03/10/2018 15:00 | 2.1628 | Developing Use Cases | 2018-10-03 15:04 | 2018-10-03 17:14
03/10/2018 17:00 | 2.6139 | Developing Use Cases | 2018-10-03 17:15 | 2018-10-03 19:52
04/10/2018 11:00 | 1.0738 | Meeting with Jan | 2018-10-04 11:56 | 2018-10-04 13:00 | Discussion on progress. Need to consider users and environments as use cases, not just resources directly. Should collect list of staff roles and duties. Consider starting on boolean formulae/type theory/PL theory development
10/10/2018 14:00 | 0.88746 | Developing Use Cases | 2018-10-10 14:42 | 2018-10-10 15:35
10/10/2018 15:00 | 2.2514 | Developing Use Cases | 2018-10-10 15:45 | 2018-10-10 18:00
10/10/2018 18:00 | 0.2989 | Developing Use Cases | 2018-10-10 18:41 | 2018-10-10 18:59
10/10/2018 19:00 | 0.44057 | Developing Use Cases | 2018-10-10 19:05 | 2018-10-10 19:32
10/10/2018 19:00 | 0.80972 | Developing Use Cases | 2018-10-10 19:32 | 2018-10-10 20:21
11/10/2018 12:00 | 1 | Meeting with Jan | 2018-10-11 12:00 | 2018-10-11 13:00 | Discussed progress of mind maps, and acknowledged that more work is required on Use Cases. Next week is last meeting for 2 weeks. Properly write out Use Cases. Define attributes for some Subjects/Users. Student persona, Student class rep ??? persona, Lecturer, Head of XXXX, Admin, Technical Think of use case for each of above (and more), what might they want to upload/download, how would they do it, what attributes might that have and the resource have. Possible other actions than just upload/download. Consider user evaluation & security evaluation.
16/10/2018 18:00 | 4.7042 | Prep for Meeting | 2018-10-16 18:31 | 2018-10-16 23:13 | Use Cases etc.
18/10/2018 12:00 | 1 | Meeting with Jan | 2018-10-18 12:00 | 2018-10-18 13:00
25/10/2018 19:00 | 1.2537 | Notes on Use Cases | 2018-10-25 19:14 | 2018-10-25 20:29
25/10/2018 23:00 | 1.0011 | Notes on Use Cases | 2018-10-25 23:03 | 2018-10-26 00:03
26/10/2018 00:00 | 1.2525 | Notes on Use Cases | 2018-10-26 00:04 | 2018-10-26 01:19
27/10/2018 14:00 | 2.2386 | Notes on Use Cases | 2018-10-27 14:33 | 2018-10-27 16:48
20/11/2018 23:00 | 1.6077 | LaTeX Policies | 2018-11-20 23:00 | 2018-11-21 00:37
21/11/2018 20:00 | 1.183 | LaTeX Attributes | 2018-11-21 20:15 | 2018-11-21 21:26
22/11/2018 00:00 | 0.53054 | LaTeX Attributes | 2018-11-22 00:03 | 2018-11-22 00:35
22/11/2018 12:00 | 0.060278 | Meeting with Jan | 2018-11-22 12:00 | 2018-11-22 12:04
22/11/2018 12:00 | 0.83111 | Meeting with Jan | 2018-11-22 12:05 | 2018-11-22 12:54
22/11/2018 14:00 | 0.91389 | LaTeX Policies | 2018-11-22 14:51 | 2018-11-22 15:45
24/11/2018 17:00 | 1.0006 | LaTeX Policies | 2018-11-24 17:55 | 2018-11-24 18:55
29/11/2018 12:00 | 1.0092 | Meeting with Jan | 2018-11-29 12:00 | 2018-11-29 13:01
03/12/2018 23:00 | 1.6613 | ABE Testing | 2018-12-03 23:09 | 2018-12-04 00:49
04/12/2018 16:00 | 1.009 | Status Report Writing | 2018-12-04 16:55 | 2018-12-04 17:56
05/12/2018 22:00 | 2.8907 | Status Report Writing | 2018-12-05 22:34 | 2018-12-06 01:28
06/12/2018 15:00 | 0.81308 | PlantUML Diagrams | 2018-12-06 15:13 | 2018-12-06 16:02
06/12/2018 16:00 | 0.78149 | PlantUML Diagrams | 2018-12-06 16:42 | 2018-12-06 17:29
06/12/2018 17:00 | 0.99331 | PlantUML Diagrams | 2018-12-06 17:42 | 2018-12-06 18:42
06/12/2018 23:00 | 0.55928 | PlantUML Diagrams | 2018-12-06 23:05 | 2018-12-06 23:38
07/12/2018 15:00 | 0.47555 | ABE Testing | 2018-12-07 15:03 | 2018-12-07 15:31
07/12/2018 16:00 | 0.23597 | ABE Testing | 2018-12-07 16:05 | 2018-12-07 16:19
07/12/2018 16:00 | 0.87426 | ABE Testing | 2018-12-07 16:27 | 2018-12-07 17:20
07/12/2018 17:00 | 0.22041 | ABE Testing | 2018-12-07 17:58 | 2018-12-07 18:11
07/12/2018 21:00 | 1.7816 | ABE Testing | 2018-12-07 21:42 | 2018-12-07 23:29
08/12/2018 14:00 | 1.9619 | Server B64 decoding work | 2018-12-08 14:02 | 2018-12-08 16:00
10/12/2018 18:00 | 1.2816 | Server Prototyping | 2018-12-10 18:51 | 2018-12-10 20:08
10/12/2018 22:00 | 4.8128 | Server Prototyping | 2018-12-10 22:19 | 2018-12-11 03:08
11/12/2018 03:00 | 0.33494 | Server Prototyping | 2018-12-11 03:15 | 2018-12-11 03:36
11/12/2018 16:00 | 2.0597 | Server Prototyping | 2018-12-11 16:43 | 2018-12-11 18:47
11/12/2018 18:00 | 1.0878 | Server Prototyping | 2018-12-11 18:47 | 2018-12-11 19:53
11/12/2018 20:00 | 0.55268 | Server Prototyping | 2018-12-11 20:51 | 2018-12-11 21:24
11/12/2018 22:00 | 0.366 | Server Prototyping | 2018-12-11 22:59 | 2018-12-11 23:21
11/12/2018 23:00 | 2.6875 | Server Prototyping | 2018-12-11 23:22 | 2018-12-12 02:04
12/12/2018 21:00 | 2.2535 | Server B64 decoding work | 2018-12-12 21:54 | 2018-12-13 00:10
13/12/2018 00:00 | 1.831 | Server B64 decoding work | 2018-12-13 00:20 | 2018-12-13 02:10
13/12/2018 12:00 | 1.1088 | Meeting with Jan | 2018-12-13 12:00 | 2018-12-13 13:07
13/12/2018 15:00 | 1.2552 | Server B64 decoding work | 2018-12-13 16:00 | 2018-12-13 17:15
17/01/2019 12:00 | 1 | Meeting with Jan | 2019-01-17 12:00 | 2019-01-17 13:00
18/01/2019 10:00 | 0.48925 | Implementing metadata extraction | 2019-01-18 10:46 | 2019-01-18 11:16
21/01/2019 17:00 | 1.8435 | Adding routes | 2019-01-21 17:57 | 2019-01-21 19:48
21/01/2019 21:00 | 2.7232 | Adding routes | 2019-01-21 21:04 | 2019-01-21 23:48
23/01/2019 19:00 | 0.23388 | Adding routes | 2019-01-23 19:17 | 2019-01-23 19:32
23/01/2019 21:00 | 2.1256 | Adding routes | 2019-01-23 21:52 | 2019-01-24
24/01/2019 11:00 | 0.73886 | Cleaning up | 2019-01-24 11:10 | 2019-01-24 11:54
24/01/2019 12:00 | 1.0156 | Meeting with Jan | 2019-01-24 12:00 | 2019-01-24 13:01
24/01/2019 18:00 | 1.5669 | Implementing metadata extraction | 2019-01-24 18:22 | 2019-01-24 19:56
24/01/2019 22:00 | 4.0829 | Implementing metadata extraction | 2019-01-24 22:16 | 2019-01-25 02:21
27/01/2019 18:00 | 0.38472 | DocStrings & cleanup | 2019-01-27 18:09 | 2019-01-27 18:32
27/01/2019 18:00 | 3.4456 | DocStrings & cleanup | 2019-01-27 18:33 | 2019-01-27 21:59
28/01/2019 16:00 | 2.0126 | Search functionality | 2019-01-28 16:27 | 2019-01-28 18:28
28/01/2019 20:00 | 0.55111 | Search functionality | 2019-01-28 20:10 | 2019-01-28 20:43
28/01/2019 21:00 | 0.63867 | Search functionality | 2019-01-28 21:30 | 2019-01-28 22:08
28/01/2019 23:00 | 1.1336 | Search functionality | 2019-01-28 23:00 | 2019-01-29 00:08
30/01/2019 11:00 | 0.83399 | Extraction functionality | 2019-01-30 11:35 | 2019-01-30 12:25
30/01/2019 16:00 | 1.1075 | Extraction functionality | 2019-01-30 16:53 | 2019-01-30 18:00
31/01/2019 12:00 | 0.95528 | Meeting with Jan | 2019-01-31 12:02 | 2019-01-31 13:00
03/02/2019 18:00 | 1.0553 | Auth functionality | 2019-02-03 18:08 | 2019-02-03 19:11
04/02/2019 16:00 | 1.7541 | Auth functionality | 2019-02-04 16:35 | 2019-02-04 18:21
04/02/2019 19:00 | 0.35971 | Auth functionality | 2019-02-04 19:51 | 2019-02-04 20:12
04/02/2019 21:00 | 2.692 | Auth functionality | 2019-02-04 21:57 | 2019-02-05 00:39
06/02/2019 22:00 | 3.537 | Bootstrap functionality | 2019-02-06 22:16 | 2019-02-07 01:48
07/02/2019 12:00 | 1 | Supervisor Meeting | 2019-02-07 12:00 | 2019-02-07 13:00 | timing.eventID=60om6db66dhjcb9o70smab9kckpj4b9p60p38bb2c4p3gcpnccq62e1gc4_R20190117T120000@google.com
07/02/2019 13:00 | 0.31421 | Policy Builder functionality | 2019-02-07 13:30 | 2019-02-07 13:49
07/02/2019 22:00 | 2.5231 | Policy Builder functionality | 2019-02-07 22:51 | 2019-02-08 01:22
10/02/2019 22:00 | 1.5287 | Policy Builder functionality | 2019-02-10 22:32 | 2019-02-11 00:04
11/02/2019 23:00 | 0.99392 | Cleaning up | 2019-02-11 23:30 | 2019-02-12 00:30
13/02/2019 22:00 | 0.26298 | Dissertation Work | 2019-02-13 22:34 | 2019-02-13 22:50
13/02/2019 23:00 | 0.42443 | Dissertation Work | 2019-02-13 23:16 | 2019-02-13 23:41
14/02/2019 00:00 | 1.483 | Dissertation Work | 2019-02-14 00:23 | 2019-02-14 01:52
14/02/2019 10:00 | 1.8445 | Dissertation Work | 2019-02-14 10:41 | 2019-02-14 12:31
16/02/2019 13:00 | 0.35976 | Markdown Work | 2019-02-16 13:20 | 2019-02-16 13:42
16/02/2019 14:00 | 0.15484 | Dissertation Work | 2019-02-16 14:38 | 2019-02-16 14:47
16/02/2019 15:00 | 0.62665 | Markdown Work | 2019-02-16 15:58 | 2019-02-16 16:36
16/02/2019 17:00 | 0.3772 | Markdown Work | 2019-02-16 17:39 | 2019-02-16 18:01
16/02/2019 18:00 | 1.037 | Dissertation Work | 2019-02-16 18:01 | 2019-02-16 19:04
17/02/2019 15:00 | 0.88371 | Dissertation Work | 2019-02-17 15:22 | 2019-02-17 16:15
18/02/2019 13:00 | 2.6131 | Dissertation Work | 2019-02-18 13:18 | 2019-02-18 15:55
21/02/2019 11:00 | 2 | Supervisor Meeting | 2019-02-21 11:00 | 2019-02-21 13:00 | timing.eventID=60om6db66dhjcb9o70smab9kckpj4b9p60p38bb2c4p3gcpnccq62e1gc4_R20190117T120000@google.com
21/02/2019 15:00 | 1.1137 | PlantUML Work | 2019-02-21 15:58 | 2019-02-21 17:05
21/02/2019 17:00 | 2.2437 | PlantUML Work | 2019-02-21 17:36 | 2019-02-21 19:51
21/02/2019 23:00 | 0.52748 | PlantUML Work | 2019-02-21 23:19 | 2019-02-21 23:51
22/02/2019 00:00 | 0.43132 | Dissertation Work | 2019-02-22 00:03 | 2019-02-22 00:29
07/03/2019 16:00 | 0.94218 | Dissertation Work | 2019-03-07 16:49 | 2019-03-07 17:45
07/03/2019 18:00 | 0.83475 | Dissertation Work | 2019-03-07 18:30 | 2019-03-07 19:21
07/03/2019 19:00 | 0.7673 | Dissertation Work | 2019-03-07 19:48 | 2019-03-07 20:34
07/03/2019 23:00 | 0.5547 | Dissertation Work | 2019-03-07 23:07 | 2019-03-07 23:41
08/03/2019 08:00 | 1.5974 | Dissertation Work | 2019-03-08 08:35 | 2019-03-08 10:11
08/03/2019 10:00 | 0.76942 | Dissertation Work | 2019-03-08 10:49 | 2019-03-08 11:35
08/03/2019 13:00 | 1.7905 | Dissertation Work | 2019-03-08 13:26 | 2019-03-08 15:14
10/03/2019 13:00 | 1.0874 | Dissertation Work | 2019-03-10 13:39 | 2019-03-10 14:44
10/03/2019 14:00 | 0.21085 | Dissertation Work | 2019-03-10 14:52 | 2019-03-10 15:05
10/03/2019 15:00 | 0.25254 | Dissertation Work | 2019-03-10 15:48 | 2019-03-10 16:03
10/03/2019 16:00 | 0.25957 | Dissertation Work | 2019-03-10 16:09 | 2019-03-10 16:25
17/03/2019 17:00 | 0.72922 | Dissertation Work | 2019-03-17 17:19 | 2019-03-17 18:03
19/03/2019 22:00 | 0.75105 | Dissertation Work | 2019-03-19 22:26 | 2019-03-19 23:11
20/03/2019 17:00 | 0.33669 | Dissertation Work | 2019-03-20 17:33 | 2019-03-20 17:53
20/03/2019 18:00 | 0.83471 | Dissertation Work | 2019-03-20 18:15 | 2019-03-20 19:06
20/03/2019 21:00 | 1.0722 | Dissertation Work | 2019-03-20 21:14 | 2019-03-20 22:19
20/03/2019 22:00 | 1.4293 | Dissertation Work | 2019-03-20 22:46 | 2019-03-21 00:11
21/03/2019 00:00 | 1.347 | Dissertation Work | 2019-03-21 00:30 | 2019-03-21 01:50
21/03/2019 17:00 | 0.75138 | Presentation Prep | 2019-03-21 17:37 | 2019-03-21 18:22
21/03/2019 19:00 | 0.27439 | Presentation Prep | 2019-03-21 19:56 | 2019-03-21 20:13
21/03/2019 21:00 | 0.48829 | Presentation Prep | 2019-03-21 21:15 | 2019-03-21 21:45
21/03/2019 22:00 | 0.49887 | Presentation Prep | 2019-03-21 22:12 | 2019-03-21 22:42
21/03/2019 22:00 | 1.5047 | Presentation Prep | 2019-03-21 22:51 | 2019-03-22 00:21 | Prep for presentation.
22/03/2019 10:00 | 0.73208 | Dissertation Work | 2019-03-22 10:01 | 2019-03-22 10:45
22/03/2019 11:00 | 0.9825 | Presentations | 2019-03-22 11:01 | 2019-03-22 12:00
22/03/2019 13:00 | 0.55554 | Dissertation Work | 2019-03-22 13:11 | 2019-03-22 13:44
22/03/2019 14:00 | 0.18556 | Dissertation Work | 2019-03-22 14:11 | 2019-03-22 14:22
22/03/2019 14:00 | 4.5658 | Dissertation Work | 2019-03-22 14:22 | 2019-03-22 18:56
22/03/2019 18:00 | 5.9317 | Dissertation Work | 2019-03-22 18:56 | 2019-03-23 00:52
23/03/2019 12:00 | 1.5506 | Dissertation Work | 2019-03-23 12:07 | 2019-03-23 13:40
23/03/2019 13:00 | 0.2925 | Dissertation Work | 2019-03-23 13:40 | 2019-03-23 13:57
23/03/2019 13:00 | 0.75859 | Dissertation Work | 2019-03-23 13:57 | 2019-03-23 14:43
23/03/2019 16:00 | 1.8772 | Dissertation Work | 2019-03-23 16:16 | 2019-03-23 18:08
23/03/2019 18:00 | 1.3933 | Dissertation Work | 2019-03-23 18:08 | 2019-03-23 19:32
23/03/2019 19:00 | 0.20387 | Dissertation Work | 2019-03-23 19:54 | 2019-03-23 20:06
23/03/2019 21:00 | 1.3495 | Dissertation Work | 2019-03-23 21:15 | 2019-03-23 22:36
24/03/2019 11:00 | 2.4329 | Dissertation Work | 2019-03-24 11:40 | 2019-03-24 14:06
24/03/2019 15:00 | 0.27663 | Dissertation Work | 2019-03-24 15:49 | 2019-03-24 16:05
24/03/2019 16:00 | 2.6246 | Dissertation Work | 2019-03-24 16:25 | 2019-03-24 19:02
24/03/2019 19:00 | 1.2842 | Dissertation Work | 2019-03-24 19:03 | 2019-03-24 20:20
24/03/2019 21:00 | 3.1169 | Dissertation Work | 2019-03-24 21:52 | 2019-03-25 00:59
25/03/2019 08:00 | 2.0506 | Dissertation Work | 2019-03-25 08:20 | 2019-03-25 10:23
25/03/2019 11:00 | 0.33818 | Dissertation Work | 2019-03-25 11:14 | 2019-03-25 11:34
25/03/2019 12:00 | 1.4739 | Dissertation Work | 2019-03-25 12:23 | 2019-03-25 13:51
25/03/2019 14:00 | 0.46086 | Dissertation Work | 2019-03-25 14:09 | 2019-03-25 14:36
25/03/2019 14:00 | 2.923 | Dissertation Work | 2019-03-25 14:58 | 2019-03-25 17:54
25/03/2019 18:00 | 1.2827 | Dissertation Work | 2019-03-25 18:01 | 2019-03-25 19:18
25/03/2019 19:00 | 1.4222 | Dissertation Work | 2019-03-25 19:24 | 2019-03-25 20:49
25/03/2019 21:00 | 1.1321 | Dissertation Work | 2019-03-25 21:22 | 2019-03-25 22:29
25/03/2019 22:00 | 1.4178 | Dissertation Work | 2019-03-25 22:44 | 2019-03-26 00:09
26/03/2019 00:00 | 0.31858 | Dissertation Work | 2019-03-26 00:24 | 2019-03-26 00:43
26/03/2019 10:00 | 2.2312 | Dissertation Work | 2019-03-26 10:21 | 2019-03-26 12:35
26/03/2019 13:00 | 0.31044 | Dissertation Work | 2019-03-26 13:26 | 2019-03-26 13:44
26/03/2019 14:00 | 1.5 | Final meeting with Jan | 2019-03-26 14:00 | 2019-03-26 15:30 | Jan de Muijnck-Hughes <jan.demuijnck-hughes@glasgow.ac.uk> has invited you to Project Meeting timing.eventID=4AEAFAD5-344C-4067-B345-C1095F152495
26/03/2019 15:00 | 0.93838 | Dissertation Work | 2019-03-26 15:56 | 2019-03-26 16:52
26/03/2019 16:00 | 1.4514 | Dissertation Work | 2019-03-26 16:59 | 2019-03-26 18:26
26/03/2019 18:00 | 1.4081 | Dissertation Work | 2019-03-26 18:38 | 2019-03-26 20:02
26/03/2019 20:00 | 3.1539 | Dissertation Work | 2019-03-26 20:37 | 2019-03-26 23:46
27/03/2019 00:00 | 2.8428 | Dissertation Work | 2019-03-27 00:09 | 2019-03-27 03:00
27/03/2019 09:00 | 3.2138 | Dissertation Work | 2019-03-27 09:13 | 2019-03-27 12:26
27/03/2019 12:00 | 3.1149 | Dissertation Work | 2019-03-27 12:43 | 2019-03-27 15:50